BTG SPORTS GROUP

# PARTNER SCHOOL
EXECUTION PLAN

A 12-month operating playbook for athlete development, sponsor activation, media exposure and measurable community impact.

PROGRAM COMMITMENT $5,000 annual school investment ¦ Up to 25 student-athletes ¦ Four workshops ¦ One media day ¦ One school/community campaign

Prepared for

BTG Sports Group / SponsorX Partner Schools

Planning Year: 2026–2027

Version 1.0  |  September 2026

# How to Use This Plan

This document converts the Partner School Package into a repeatable delivery system. The school and BTG should approve the annual calendar during kickoff, then use the monthly workplan, service playbooks and scorecard to manage execution.

| AT A GLANCE | COMMITMENT |
| --- | --- |
| Annual investment | $5,000 per partner school |
| Capacity | Up to 25 student-athletes |
| Program term | 12 months from kickoff |
| Primary school lead | Athletic Director or designated program coordinator |
| Primary BTG lead | Partner School Program Manager |
| Core output | Prepared athletes, sponsor-ready opportunities, one approved campaign and an impact report |

## Operating Principles

School approval comes first. All schedules, athletes, sponsors, content and campaigns move through designated school approval.

Student-athlete safety and eligibility are non-negotiable. Parent/guardian consent, school policy and applicable athletic-association rules govern participation.

Education precedes monetization. Athletes complete readiness training before being presented for sponsor opportunities.

No guaranteed sponsorships or media placements. BTG develops opportunities and provides selected editorial exposure based on fit and approval.

Document the work. Attendance, approvals, sponsor contacts, content releases and outcomes are recorded throughout the year.

## Table of Contents

1.  Program Outcomes and Success Measures

2.  Governance, Roles and Communication

3.  12-Month Implementation Roadmap

4.  Service-by-Service Execution Playbooks

5.  Workshop Curriculum

6.  Athlete Readiness and Safeguards

7.  Sponsor Outreach and Campaign Activation

8.  Media and Content Operations

9.  Budget and Resource Plan

10.  Measurement, Reporting and Quality Control

11.  Risk Management and Issue Escalation

12.  90-Day Launch Plan

13.  Appendices: Checklists, Forms and Templates

# 1. Program Outcomes and Success Measures

PRIMARY OUTCOME Build a school-approved pathway that prepares student-athletes for NIL, branding, money, media and career decisions while connecting appropriate local businesses to positive school and community campaigns.

| OUTCOME AREA | YEAR-ONE TARGET | EVIDENCE |
| --- | --- | --- |
| Participation | 20–25 enrolled; at least 80% complete the program | Roster, consent and attendance records |
| Learning | Four workshops delivered; 80% average attendance | Sign-ins, pre/post checks and evaluations |
| Readiness | 100% assessed; at least 15 athletes reach “Sponsor Ready” status | Profiles, readiness rubric and action plans |
| Sponsor pipeline | 30 qualified local businesses researched; 12 contacted; 4 meetings | CRM activity and meeting notes |
| Campaign | One school-approved community or sponsor campaign completed | Brief, approvals, assets and recap |
| Content | One media day; 20+ usable athlete/program assets | Shot list, releases and content library |
| Exposure | Selected BTG Sports Talk / iMC Network features | Published links and audience metrics |
| Impact | Year-end report delivered within 30 days of program close | Final dashboard and stakeholder feedback |

## Balanced Scorecard

| DIMENSION | METRIC | GREEN | WATCH | CORRECTIVE ACTION |
| --- | --- | --- | --- | --- |
| Delivery | Milestones on time | ≥90% | 75–89% | Rebaseline dates and owners |
| Engagement | Workshop attendance | ≥80% | 65–79% | Coach/parent follow-up |
| Readiness | Sponsor-ready athletes | ≥60% | 40–59% | Targeted coaching sessions |
| Pipeline | Qualified sponsor meetings | ≥4 | 2–3 | Increase outreach volume/referrals |
| Compliance | Required approvals on file | 100% | Any gap | Pause affected activity |
| Satisfaction | School rating | ≥4.3/5 | 3.7–4.2 | 30-day improvement plan |

# 2. Governance, Roles and Communication

| ROLE | CORE ACCOUNTABILITY | TYPICAL OWNER |
| --- | --- | --- |
| Executive Sponsor | Relationship health, escalations and renewal | BTG executive lead |
| Program Manager | Calendar, deliverables, records, dashboard and meetings | BTG Partner School PM |
| School Coordinator | School approvals, facilities, roster and internal communication | AD/designee |
| Workshop Lead | Curriculum delivery and learning evaluation | BTG facilitator |
| Athlete Relations Lead | Profiles, assessments and athlete follow-up | BTG athlete manager |
| Sponsor Lead | Prospect list, outreach, proposals and CRM | SponsorX business development |
| Media Lead | Media day, editing, approvals and publishing calendar | BTG Sports Talk / iMC |
| Safeguarding Contact | Consent, conduct, incident escalation and privacy | School + BTG designees |

## Meeting Cadence

| MEETING | PARTICIPANTS | CADENCE | PURPOSE |
| --- | --- | --- | --- |
| Kickoff | BTG + school leadership | Once, 60 minutes | Confirm goals, calendar, policies and approvals |
| Operations check-in | PM + school coordinator | Monthly, 30 minutes | Status, upcoming work, risks and decisions |
| Campaign working session | School + sponsor + BTG | As needed | Approve brief, assets, logistics and responsibilities |
| Quarterly review | Leadership + PM | Quarterly, 45 minutes | Review scorecard and adjust the plan |
| Year-end review | All leads | Once, 60 minutes | Present impact, lessons and renewal options |

## Decision Rights

School: final approval over student participation, campus access, school marks, team schedules and school-facing communications.

Parent/guardian: consent for minors’ participation, recording, profile publication and campaign involvement.

Athlete: voluntary participation and approval of individual profile facts and assigned deliverables.

BTG/SponsorX: sponsor qualification, program delivery, production standards, platform editorial decisions and contract administration.

Sponsor: approval of purchased campaign deliverables and brand assets, within the school-approved brief.

# 3. 12-Month Implementation Roadmap

| MONTH | PHASE | KEY ACTIONS | REQUIRED OUTPUT |
| --- | --- | --- | --- |
| 1 | Align | Kickoff; policies; roster criteria; master calendar; baseline survey | Signed launch checklist and calendar |
| 2 | Enroll | Recruit up to 25 athletes; collect consent; baseline profiles | Verified roster and athlete files |
| 3 | Prepare I | Workshop 1: NIL awareness; begin readiness assessments | Attendance, quiz and assessment progress |
| 4 | Prepare II | Workshop 2: financial literacy; finish initial assessments | Learning results and action plans |
| 5 | Build brands | Workshop 3: personal branding; profile coaching | Approved athlete profile drafts |
| 6 | Create | Media/content day; organize and review assets | Approved content library |
| 7 | Prepare IV | Workshop 4: media readiness + career preparation | Completion status and mock-interview scores |
| 8 | Prospect | Build 30-business target list; qualify and prioritize | Sponsor pipeline and outreach materials |
| 9 | Outreach | Contact prospects; discovery meetings; match opportunities | Meeting notes and opportunity shortlist |
| 10 | Design | Select sponsor/community concept; develop brief and approvals | Signed campaign brief and production plan |
| 11 | Activate | Launch campaign; capture participation and content | Delivered campaign and evidence file |
| 12 | Report | Measure results; present year-end report; renewal meeting | Impact report and next-year decision |

## Stage Gates

| GATE | MAY PROCEED WHEN… | APPROVER |
| --- | --- | --- |
| G1 – Launch ready | Contacts, calendar, policies and facilities are confirmed | BTG PM + school coordinator |
| G2 – Athlete enrolled | Consent, eligibility acknowledgement and baseline data are complete | School coordinator |
| G3 – Sponsor ready | Readiness score meets threshold and athlete accepts expectations | Athlete lead + school |
| G4 – Campaign approved | Sponsor, school, athlete and usage terms are documented | Authorized parties |
| G5 – Publish ready | Final assets, names, claims and releases are approved | Media lead + school |
| G6 – Closeout ready | Metrics and expenses are reconciled; issues are resolved | BTG executive lead |

# 4. Service-by-Service Execution Playbooks

## 4.1 School Onboarding and Program Planning

Purpose: Establish shared expectations, contacts, safeguards and a realistic calendar before athlete activity begins.

Send welcome packet and data request within two business days of agreement.

Hold a 60-minute kickoff with school leadership, athletics, communications and safeguarding contacts.

Confirm priority sports, athlete selection method, blackout dates, available space and technology.

Collect school brand rules, media rules, visitor procedures and applicable NIL/eligibility guidance.

Issue the master calendar, responsibility matrix and approval path within five business days.

| REQUIRED RECORDS | ACCEPTANCE STANDARD |
| --- | --- |
| Launch checklist; contact directory; approved calendar; policy summary; issue log. | Complete by Day 15; 100% required information received. |

## 4.2 Four Athlete-Development Workshops

Purpose: Deliver a progressive learning sequence that moves athletes from awareness to practical readiness.

Schedule four 75–90 minute sessions, ideally 6–8 weeks apart.

Use sign-in, pre/post knowledge checks and one applied exercise per session.

Provide a take-home worksheet and a specific action due before the next session.

Offer one make-up method: recorded recap, virtual session or supervised worksheet.

Report attendance, learning scores and follow-up needs within five business days.

| REQUIRED RECORDS | ACCEPTANCE STANDARD |
| --- | --- |
| Facilitator guide; slides; worksheets; attendance; evaluations; action tracker. | Four sessions completed; ≥80% average attendance; ≥20% knowledge improvement. |

## 4.3 Parent and Coach Information Session

Purpose: Align adults around expectations, safeguards, eligibility, time demands and family support.

Host during Month 1 or 2, before public athlete profiles.

Explain program scope, what is and is not guaranteed, approvals and communications.

Review responsible social media, compensation basics, academic/team responsibilities and reporting concerns.

Collect questions; publish an FAQ and escalation contact within three business days.

| REQUIRED RECORDS | ACCEPTANCE STANDARD |
| --- | --- |
| Agenda; presentation; attendance; FAQ; acknowledgements. | At least one parent/guardian contact per minor; coaches briefed. |

## 4.4 Athlete Profiles and Readiness Assessment

Purpose: Create accurate basic profiles and identify coaching required before sponsor consideration.

Collect verified biography, sport, position/event, interests, achievements and contact routing.

Audit social presence only with authorized access; do not request passwords.

Score professionalism, communication, reliability, brand clarity, compliance awareness and support readiness.

Assign status: Developing, Nearly Ready or Sponsor Ready.

Review profile facts with athlete and school; refresh at least quarterly.

| REQUIRED RECORDS | ACCEPTANCE STANDARD |
| --- | --- |
| Profile; headshot; readiness score; improvement plan; approval record. | 100% assessed; no public profile without approvals. |

## 4.5 Athlete Media/Content Day

Purpose: Produce consistent, school-approved assets and teach athletes how to represent themselves.

Approve date, location, shot list, interview prompts, dress code and releases four weeks ahead.

Run timed stations: check-in, portrait, action/lifestyle, interview and sponsor-neutral clips.

Use a naming convention and asset log; back up files the same day.

Complete first review in 10 business days; route school/athlete approvals before use.

Deliver approved selections and a 30-day publishing queue.

| REQUIRED RECORDS | ACCEPTANCE STANDARD |
| --- | --- |
| Call sheet; releases; photos; video clips; transcripts; asset log. | ≥20 approved assets; 100% files traceable to releases. |

## 4.6 Local Business Sponsor Outreach

Purpose: Build a qualified community-business pipeline around school-aligned opportunities.

Define excluded industries and sponsor criteria with the school.

Research 30 prospects across food, health, retail, auto, finance, education and professional services.

Prioritize proximity, community reputation, youth alignment, activation ability and budget fit.

Use a three-touch sequence and log every contact in the CRM.

Never promise athlete participation, sales, reach or exclusivity before written approval.

| REQUIRED RECORDS | ACCEPTANCE STANDARD |
| --- | --- |
| Target list; outreach messages; CRM; meeting briefs; opportunity recommendations. | 30 qualified; 12 contacted; 4 meetings; 1 campaign candidate. |

## 4.7 One School/Community Campaign

Purpose: Turn education and sponsor interest into one manageable, visible impact initiative.

Select one concept against school priorities, athlete capacity, safety and sponsor fit.

Create a one-page brief covering objective, audience, roles, deliverables, rights, budget and measurement.

Secure approvals and agreements before production or public announcement.

Run a production checklist and day-of command structure.

Close with proof of delivery, results, thank-yous and lessons learned.

| REQUIRED RECORDS | ACCEPTANCE STANDARD |
| --- | --- |
| Approved brief; agreements; run-of-show; assets; recap; metric sheet. | 100% committed deliverables completed; no unresolved safety/compliance issue. |

## 4.8 BTG Sports Talk / iMC Network Exposure

Purpose: Extend selected program stories through credible editorial coverage.

Identify stories with educational, community or athlete-development value.

Conduct editorial review; confirm facts, permissions and school timing.

Prepare interview participants, talking points and contingency dates.

Publish only approved assets; archive links and performance metrics.

Separate editorial consideration from purchased sponsor rights.

| REQUIRED RECORDS | ACCEPTANCE STANDARD |
| --- | --- |
| Pitch sheet; interview prep; approvals; published links; metrics. | At least two story pitches; selected coverage subject to editorial approval. |

## 4.9 Year-End Impact Report

Purpose: Provide a credible record of participation, activity, outreach, outcomes and lessons.

Freeze data 10 business days after final activity.

Validate attendance, readiness, sponsor activity, published content, campaign delivery and expenses.

Collect school, athlete and sponsor feedback.

Draft results, stories, gaps, recommendations and next-year options.

Present within 30 days of program end and document renewal decision.

| REQUIRED RECORDS | ACCEPTANCE STANDARD |
| --- | --- |
| Executive summary; dashboard; activity record; stories; recommendations. | Delivered on time; school rating ≥4.3/5; renewal decision recorded. |

# 5. Workshop Curriculum

## Workshop 1 — NIL Awareness and Athlete Responsibility

Learning objective: Understand NIL basics, distinguish opportunity from risk and know when to ask for help.

| SUGGESTED AGENDA | MINUTES |
| --- | --- |
| Welcome and pre-check | 10 |
| Instruction and discussion | 25 |
| Applied exercise | 25 |
| Scenario or practice | 15 |
| Post-check, assignment and close | 10 |

### Core topics

What NIL is and is not

School/state/association rules and reporting

Contracts, exclusivity, usage rights and conflicts

Scams, prohibited categories and red flags

Scenario exercise: accept, pause or decline

PARTICIPANT OUTPUT Completed opportunity checklist and personal questions list.

## Workshop 2 — Financial Literacy

Learning objective: Build habits for managing irregular income, taxes, saving and family expectations.

| SUGGESTED AGENDA | MINUTES |
| --- | --- |
| Welcome and pre-check | 10 |
| Instruction and discussion | 25 |
| Applied exercise | 25 |
| Scenario or practice | 15 |
| Post-check, assignment and close | 10 |

### Core topics

Gross pay vs. take-home pay

Simple 50/30/20 planning adapted for athletes

Taxes and recordkeeping

Banking, credit, fraud and professional advisors

Budget exercise using a sample campaign payment

PARTICIPANT OUTPUT One-page personal money plan and document checklist.

## Workshop 3 — Personal Branding

Learning objective: Define a credible identity that supports sport, school, community and career goals.

| SUGGESTED AGENDA | MINUTES |
| --- | --- |
| Welcome and pre-check | 10 |
| Instruction and discussion | 25 |
| Applied exercise | 25 |
| Scenario or practice | 15 |
| Post-check, assignment and close | 10 |

### Core topics

Values, audience and authentic story

Social profile audit and digital footprint

Bio writing, content pillars and posting boundaries

Sponsor fit and saying no

Profile lab and peer feedback

PARTICIPANT OUTPUT Approved short bio, three content pillars and profile improvement actions.

## Workshop 4 — Media Readiness and Career Preparation

Learning objective: Communicate confidently in interviews and connect sports experience to future careers.

| SUGGESTED AGENDA | MINUTES |
| --- | --- |
| Welcome and pre-check | 10 |
| Instruction and discussion | 25 |
| Applied exercise | 25 |
| Scenario or practice | 15 |
| Post-check, assignment and close | 10 |

### Core topics

Interview structure and message discipline

On-camera presence and difficult questions

Email, voicemail and meeting etiquette

Resume/LinkedIn basics and transferable skills

Recorded mock interview and feedback

PARTICIPANT OUTPUT Mock-interview scorecard, elevator pitch and 90-day development goal.

# 6. Athlete Readiness and Safeguards

## Readiness Scoring Rubric

| DIMENSION | 1 – DEVELOPING | 3 – FUNCTIONAL | 5 – STRONG |
| --- | --- | --- | --- |
| Reliability | Misses deadlines | Usually responsive | Consistently early/prepared |
| Communication | Needs heavy prompting | Can answer clearly | Confident and audience-aware |
| Brand clarity | No defined interests/values | Basic identity defined | Distinct, authentic positioning |
| Digital conduct | Material concerns | Generally appropriate | Consistent and sponsor-safe |
| Compliance awareness | Does not recognize risks | Uses checklist with help | Identifies issues and escalates |
| Support system | Unclear adult support | Named parent/coach contact | Active, responsive support team |

STATUS RULE Sponsor Ready: 24–30 points with no dimension below 3. Nearly Ready: 18–23 points. Developing: below 18 or any unresolved conduct, consent, eligibility or safeguarding concern.

## Required Safeguards

Roster verification and school eligibility acknowledgement.

Parent/guardian consent for minors and athlete assent.

Media release with permitted channels, term and revocation procedure.

No direct one-to-one adult/minor communications outside approved channels.

No athlete financial, medical, academic or family data included in sponsor materials unless specifically authorized.

No sponsor use of school marks, uniforms or facilities beyond written permission.

Written disclosure of deliverables, compensation, usage rights, term, exclusivity and cancellation.

Incident reporting to the school and BTG safeguarding contacts on the same business day.

# 7. Sponsor Outreach and Campaign Activation

## Sponsor Qualification Score

| CRITERION | WEIGHT | QUESTION |
| --- | --- | --- |
| School/community alignment | 25% | Does the business support youth, education, athletics or local families? |
| Reputation and safety | 25% | Is the company appropriate and free of material concerns? |
| Activation fit | 20% | Can it offer a useful product, service, venue, expertise or funding? |
| Budget/timing | 15% | Can it fund or support the approved concept this year? |
| Story value | 10% | Is there an authentic local story worth sharing? |
| Execution capacity | 5% | Can the sponsor meet approval and production deadlines? |

## Three-Touch Outreach Sequence

| TIMING | CHANNEL | MESSAGE FOCUS | NEXT STEP |
| --- | --- | --- | --- |
| Day 1 | Email | School-aligned opportunity and community benefit | Request 20-minute discovery call |
| Day 4 | Phone/voicemail | Relevance, timing and concise proof point | Confirm interest or correct contact |
| Day 10 | Email/social | Specific activation concept and close-the-loop note | Meeting, nurture or close |

## Campaign Development Workflow

Concept screen: objective, audience, athlete burden, school fit, sponsor fit and measurable result.

Discovery: sponsor goals, offer, budget, geography, timing and decision process.

Brief: scope, deliverables, content, rights, approvals, logistics, safety and metrics.

Agreement: authorized signatures, payment terms, cancellation, usage rights and compliance responsibilities.

Production: schedule, call sheet, assets, responsible owners and contingency plan.

Activation: execute, monitor safety and document delivery.

Closeout: approve final content, reconcile deliverables, report metrics and collect feedback.

## Recommended Campaign Formats

| CONCEPT | BEST USE | EXAMPLE OUTPUT |
| --- | --- | --- |
| Game-Day Fit | Apparel, retail, grooming or wellness partner | Athlete style profiles + community collection |
| What’s Your Pregame Meal? | Restaurant, grocer or nutrition partner | Short interviews + healthy-meal activation |
| School Supply Assist | Bank, retailer or professional services | Athlete-led supply drive |
| Youth Skills Day | Health, fitness or sporting-goods partner | Clinic, mentoring and recap content |
| Career Beyond the Game | Employer, college or trade partner | Career panel + athlete profile features |
| Community Cleanup | Home services, waste or construction partner | Service day + impact story |

# 8. Media and Content Operations

| STAGE | CONTROL | OWNER |
| --- | --- | --- |
| Pre-production | Approved roster, release status, shot list, interview questions, brand rules and schedule | Media lead + school |
| Capture | Check-in, release verification, file naming, safe supervision and backup | Producer |
| Edit | Selects, accurate captions, music/license check, sponsor mark check | Editor |
| Approval | Athlete/guardian, school and sponsor approval as applicable | Program manager |
| Publish | Final channel, copy, tags, timing and comment monitoring | Media lead |
| Archive | Source files, approvals, final assets, links and metrics | Program coordinator |

## Content Naming Convention

FILE NAMING SCHOOL_YYYYMMDD_ATHLETELAST_FIRST_ASSETTYPE_VERSION_APPROVALSTATUS.ext • Example: CARROLL_20261014_SMITH_JADA_INTERVIEW_V2_APPROVED.mp4

## Media-Day Station Plan

| STATION | MINUTES/ATHLETE | OUTPUT |
| --- | --- | --- |
| 1. Check-in and release | 3 | Verified participation |
| 2. Portraits | 6 | Headshot + vertical/horizontal portraits |
| 3. Action/lifestyle | 8 | Sport and personality assets |
| 4. Interview | 8 | Two short-form answers + clean audio |
| 5. Review and exit | 3 | Name/pronunciation check and next steps |

# 9. Budget and Resource Plan

The following is an internal delivery allocation for the $5,000 annual package. It is a management baseline, not a promise that each category will be invoiced separately. Adjust within the total while protecting the required deliverables.

| COST CENTER | PLANNED | % | CONTROL |
| --- | --- | --- | --- |
| Program management and school onboarding | $900 | 18% | Calendar, meetings, records and reporting |
| Four workshops | $1,200 | 24% | Facilitation, materials and evaluation |
| Athlete profiles/readiness | $650 | 13% | Intake, scoring and coaching |
| Media/content day | $900 | 18% | Production and initial editing |
| Sponsor outreach | $550 | 11% | Research, CRM and meetings |
| Campaign planning/activation | $500 | 10% | Brief, coordination and recap |
| Reporting/admin reserve | $300 | 6% | Impact report and contingencies |
| TOTAL | $5,000 | 100% | Annual package ceiling |

BUDGET BOUNDARY External venue, travel, paid advertising, specialized production, athlete compensation, merchandise, printing beyond standard materials and campaign hard costs are not assumed in the $5,000 package unless specifically written into the agreement.

## Minimum Staffing Assumptions

| FUNCTION | ESTIMATED ANNUAL HOURS | PEAK PERIOD |
| --- | --- | --- |
| Program manager | 45–55 | Months 1, 10–12 |
| Workshop facilitator | 20–28 | Months 3, 4, 5 and 7 |
| Athlete relations | 20–25 | Months 2–7 |
| Sponsor business development | 25–35 | Months 8–11 |
| Media team | 24–36 | Months 6 and 11 |
| Executive oversight | 8–12 | Kickoff, quarterly reviews and closeout |

# 10. Measurement, Reporting and Quality Control

## Monthly Dashboard Fields

Roster: enrolled, active, withdrawn and completed.

Delivery: milestones due, completed, late and blocked.

Engagement: workshop attendance, make-ups and assignments.

Readiness: average score, status distribution and unresolved actions.

Sponsor pipeline: prospects by stage, meetings, proposals and estimated value.

Content: assets captured, approved, published and performance.

Campaign: deliverables, budget, attendance/reach and community result.

Risk: open issues, severity, owner, due date and resolution.

Satisfaction: school, athlete, parent and sponsor feedback.

## Quality Review Before Every Major Activity

| CHECK | PASS STANDARD |
| --- | --- |
| Scope | Activity matches the signed package or an approved change. |
| People | Owners, participants and emergency contacts are confirmed. |
| Permission | Required school, parent/guardian, athlete and sponsor approvals are documented. |
| Content | Names, facts, logos, claims, music and rights are verified. |
| Logistics | Date, space, access, equipment, staffing and backup plan are confirmed. |
| Measurement | Attendance and outcome measures are ready before launch. |
| Closeout | Files, expenses, evidence and follow-ups have an assigned owner/date. |

## Year-End Report Structure

Executive summary and school priorities

Participant profile and completion

Workshop delivery and learning results

Athlete readiness outcomes

Sponsor outreach activity and opportunity status

Campaign story, deliverables and results

BTG/iMC media exposure and performance

Financial summary and in-kind value

Feedback, challenges and corrective actions

Recommendations and renewal options

# 11. Risk Management and Issue Escalation

| RISK | PREVENTION | IMMEDIATE RESPONSE |
| --- | --- | --- |
| Missing consent | Consent tracker; no same-day exceptions | Remove athlete from affected activity |
| Eligibility conflict | School review before sponsor presentation | Pause and refer to school/compliance lead |
| Unsafe/inappropriate sponsor | Qualification screen and excluded categories | Stop outreach/activation and escalate |
| Missed athlete deliverable | Clear deadlines, reminders and backup participants | Coach athlete; revise scope if needed |
| Content/privacy error | Fact check, release check and approval workflow | Unpublish where possible; notify parties |
| Low attendance | Calendar alignment, coach reminders and make-ups | Offer approved make-up and engagement plan |
| Sponsor nonpayment | Written payment schedule and production gate | Pause sponsor-specific work per agreement |
| Weather/facility disruption | Backup date/location and communication tree | Activate contingency plan |
| Reputational incident | Monitoring and designated spokesperson | Preserve facts; escalate same business day |

## Escalation Levels

| LEVEL | EXAMPLE | RESPONSE TIME | AUTHORITY |
| --- | --- | --- | --- |
| 1 – Routine | Schedule change, minor missed task | 2 business days | Program manager |
| 2 – Material | Repeated delay, sponsor concern, disputed deliverable | Same business day | BTG executive + school lead |
| 3 – Critical | Safety, privacy, eligibility or legal concern | Immediately | Pause activity; authorized leadership/legal |

# 12. 90-Day Launch Plan

| WINDOW | ACTIONS | OWNER | PROOF OF COMPLETION |
| --- | --- | --- | --- |
| Days 1–10 | Name leads; kickoff; collect policies; confirm goals and blackout dates | BTG PM + school | Kickoff notes and contact list |
| Days 11–20 | Approve calendar; define athlete selection; launch parent/coach communication | School coordinator | Calendar and invitation |
| Days 21–30 | Enroll athletes; collect consent; administer baseline survey | Athlete lead | Verified roster |
| Days 31–45 | Complete basic profiles; hold parent/coach session | Athlete lead + facilitator | Profile drafts and FAQ |
| Days 46–60 | Deliver Workshop 1; score first readiness domains | Facilitator | Attendance and results |
| Days 61–75 | Athlete coaching; confirm media-day date and production needs | Athlete/media leads | Action tracker and call-sheet draft |
| Days 76–90 | Deliver Workshop 2 or complete scheduling; quarterly review | PM + school | Quarterly scorecard and decisions |

## First 30-Day Checklist

☐ Agreement and payment schedule confirmed

☐ BTG and school points of contact named

☐ Kickoff completed

☐ School priorities and excluded sponsor categories documented

☐ Annual calendar and facilities approved

☐ Athlete selection criteria announced

☐ Consent and media-release forms issued

☐ CRM, roster tracker, asset log and issue log created

☐ Baseline survey ready

☐ First workshop and parent/coach session scheduled

# 13. Appendices: Checklists, Forms and Templates

## Appendix A — Kickoff Agenda

| TIME | TOPIC | DECISION/OUTPUT |
| --- | --- | --- |
| 0–10 min | Introductions and outcomes | Named leads |
| 10–20 min | School priorities and athlete population | Program focus |
| 20–30 min | Calendar, facilities and blackout dates | Draft master calendar |
| 30–40 min | Policies, consent, media and sponsor restrictions | Approval path |
| 40–50 min | Data, communications and success measures | Reporting plan |
| 50–60 min | Risks, open questions and next steps | Action log |

## Appendix B — Athlete Intake Fields

☐ Legal name; preferred name; pronunciation; graduation year

☐ Sport, team, position/event, jersey number and verified achievements

☐ School email and approved family contact route

☐ Interests, values, community involvement and career interests

☐ Social handles voluntarily supplied for review; no passwords

☐ Prior sponsor/endorsement relationships or restrictions

☐ Accessibility, scheduling or support needs

☐ Athlete and parent/guardian consent; media permissions

☐ School verification and date last reviewed

## Appendix C — Campaign Brief Fields

| FIELD | REQUIRED ENTRY |
| --- | --- |
| Campaign name | Clear working title |
| Objective | One measurable business/community result |
| Audience | Primary and secondary groups |
| Sponsor offer | Product, service, funding or in-kind support |
| Athlete role | Voluntary deliverables and time commitment |
| School role | Facilities, approvals and communications |
| Deliverables | Exact content, event and reporting outputs |
| Usage rights | Channels, geography, term, paid use and ownership |
| Budget/payment | Fee, hard costs, timing and responsibility |
| Schedule | Approvals, production, launch and closeout dates |
| Safeguards | Consent, supervision, eligibility and incident contacts |
| Measurement | Reach, participation, leads, donations or other outcomes |

## Appendix D — Monthly Status Report

| SECTION | WHAT TO REPORT |
| --- | --- |
| Overall status | Green / Watch / At Risk with one-sentence rationale |
| Completed | Milestones and deliverables completed this month |
| Next | Work due during the next 30 days |
| Metrics | Attendance, readiness, pipeline, content and campaign numbers |
| Decisions | Items requiring school or BTG approval |
| Risks | Issue, owner, due date and mitigation |
| Budget | Planned, actual and forecast variance |

## Appendix E — Change Control

USE WHEN SCOPE CHANGES Document the requested change, reason, affected deliverables, added cost, revised dates and required approvals. No expanded work begins until authorized in writing.

| CHANGE REQUEST | IMPACT | DECISION |
| --- | --- | --- |
| Requested by / date | Deliverables affected | Approve / decline / revise |
| Description and reason | Schedule and staffing impact | Authorized names and dates |
| Requested new outcome | Cost or in-kind impact | Updated plan version |

## Appendix F — Closeout Checklist

☐ All workshops and make-ups recorded

☐ Athlete profiles updated and access reviewed

☐ Sponsor contacts and opportunities reconciled

☐ Campaign deliverables and payments reconciled

☐ Published content links and metrics archived

☐ Open issues resolved or formally transferred

☐ Feedback collected

☐ Impact report approved and presented

☐ Renewal decision and next-step date documented

☐ Files retained or deleted according to policy

# Execution Standard

The Partner School Package succeeds when the school can see a clear record of preparation, participation, responsible sponsor engagement and community value—not simply a collection of events.

IMMEDIATE NEXT ACTION Assign the BTG Program Manager and school coordinator, then schedule the 60-minute kickoff. The approved master calendar and verified athlete enrollment process are the two dependencies for every service that follows.

BTG Sports Group  |  SponsorX  |  Beyond the Game